## Slide 1
The 22nd M&E Learning Forum
M&E Framework

## Slide 2: Objective
1- To understand about key term in result chain
2- To understand about Monitoring & Evaluation framework/plan
3- To develop and practice on Monitoring & Evaluation Framework/plan

## Slide 3: Group Discussion by Table
Based on your experiences, after project proposal approved, what do you do (as M&E roles)?

## Slide 4: Role M&E after Project approved
1- Develop M&E framework /plan
2- Develop indicator tracking table or sheet
3- Develop activities tracking table or sheet
4- Develop tool for collecting data to update indicators
5- Develop databased for data management,.. Etc..

## Slide 5: Key term in result chain
Activity
Output
Use of output
Outcome
Impact
Result chain

## Slide 6: Definition key term in result chain
Activity: the tasks that need to be carried out to deliver the planned outputs through the use of inputs (e.g. build wells)
Output : the direct/ tangible results (goods, services, knowledge) that the project delivers, and which are largely under project management’s control. (e.g. Clean drinking water is provided)
Use of output : the way in which outputs should be used by the target group in order to deliver desired outcome.
(e.g Families use water for cooking and drinking... )

## Slide 7: Key term in result chain
4. Outcome: short and medium-term change for the target groups. The outcome is the result of the use of outputs, which have a benefit for the target group. ( e.g. Illnesses have decreased and hygiene has improved)
5. Impact: Long-term, intended and unintended, positive and negative, effects of the project on people, institutions and the physical environment. It can be observed in the course of a project as well as after the project has ended. (e.g. Child mortality has declined, medical costs have decreased “ living conditions have improved” )
6. Result chain: A results chain describes the logical connection between inputs, activities, outputs, their use and the resulting outcomes and impacts.

## Slide 8: Example: Visualising the intervention logic – the “Effect Chain”
Finances,
Staff, etc…
Clean drinking water is provided
Families use water for cooking and drinking
Illnesses have decreased and hygiene has improved
Child mortality has declined, medical costs have decreased “ living conditions have improved”
Inputs
Activities
Output
Use of output
Outcome
Impacts
EFFECTS
Wells are built..
RESULTS (According to DAC – but without „use of Output“ level)

## Slide 9: M&E Framework/plan
Program Logic | Performance Indicator | Definition | Unit of Measure | Disaggre- gated by | Data Frequency | Data source | Data Collection Method | Data Collection Tools | Responsible person | Baseline year | Baseline value | FY# Target | FY# Target | FY# Target | LoP Target
Goal/ Impact |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Ob/ Outcome |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Output |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 

## Slide 10: Group Practice
Developing M&E Framework/Plan
(1.30- 3.30pm include presentation)

## Slide 11: Group Practice
Developing M&E Framework/Plan
(1.30- 3.30pm include presentation)

## Slide 12: M&E package
1- M&E Framework/Plan
2- Performance Indicator Tracking Sheet/Table (PITS/T)
3- Activity Tracking Sheet/Table (ATS/T)
4- M&E Tool (data collection)

## Slide 13: Developing M&E Tool (data collection)
Specific Objectives | Indicators | Info needed | source | methods
Increased capacity of CSOs for innovative response to development challenges | SO1.1: At least 50% of the NGO Applicants engaged in GPP Certification System complied with GPP Standards | # NGOs applicant # NGOs has been desk review by GPP team # NGOs assessment my GPP team # NGOs engage in GPP Certification system complied with GPP standard # Result /change after PGPP | - GPP database system - GPP applicant - SRI | Desk review KII with GPP applicant

## Slide 14: Thanks for your attention!