## Livelihood_M&E Plan (hidden)
RF Level | Intended Result | Performance Indicator | Definition | Unit of Measure | Disaggregated by | Data Frequency | Data Source | Data Collection Method | Data Collection Tools | Responsible Person | Baseline Year | Baseline Value | FY # Target | FY # Target | FY # Target | Life of Program Target
Purpose/ Outcome | The income of targeted small farm households in 20 target districts of 5 provinces increased by 30% by 2020 | Average annual income from organic rice of small farm households of the target provice increased by 30% by the end of 2020 | Organic farming: no chemical fertilizer and pesticide use in farming applied by target households. Small Farm households: households in the target villages have farm land less than 3ha and depend on agriculture for income | % of Average annual income increase from Baseline | Gender-head HH | yearly (every June) | Project staff collect data from the target households by using questionnaires | Household survey | Survey suestionnaire | Project staff | 2017 | 5 | 10% | 20% | 30% | 30%
| NGO capacity increased innovative responses to development challenges by 50% by the end of 2022. | At least 50% of capacitated NGOs integrated lessons gained from capacity development | NGO capacity: improvement of M&E, finance, human resource and ICT system and practice result from their engagement in these ralated for a CCC organized | % of NGO capacity increase from baseline | Man & Woman | Annual (every Nov) | CD team collect data from the target NGOs by using survey form | NGO survey | Survey questionnaire | CD team | 2020 | 25% | 35% | 45% | 50% | 50%

## M&E Template
Program Logic | Performance Indicator | Definition | Unit of Measure | Disaggregated by | Data Frequency | Data Source | Data Collection Method | Data Collection Tools | Responsible Person | Baseline Year | Baseline Value | FY2017 # Target | FY2018 # Target | FY2019 # Target | FY2020 # Target | FY2021 # Target | Life of Program Target
Goal/ Impact
Purpose/ Outcome: Increased capacity of CSOs for innovative responses to development challenges. | At least 65% of capacitated NGOs and CBOs integrated lessons gained from capacity development, learning exchange platform, and innovative practice. | Improvement of the M&E, Finance, Human Resources, and ICT system and practice of NGOs and CBOs resulted from their engagement in these related fora CCC organised. | % of NGO capacity increase from baseline | LNGO FNGO CBO | Annually (every Nov) | NGO members | NGO survey | Survey questionnaire | CD team | December 2017 | 50% | 50% | 55% | 60% | 65% | 65% | 65%
Output

## PITS
Performance Indicator Tracking Sheets/Table
INDICATOR |  | Type of Indicator | Baseline | Y1 | [5 empty] | Y2 | [5 empty] | Y3 | [5 empty] | Y4 | [5 empty] | Y5 | [5 empty] | Life of Project (LOP)
|  |  |  | Target | S1 | S2 | Progress |  | Justification | Target | S1 | S2 | Progress |  | Justification | Target | S1 | S2 | Progress |  | Justification | Target | S1 | S2 | Progress |  | Justification | Target | S1 | S2 | Progress |  | Justification | Target | To Date |  | Justification
[5 empty] | Actual | Actual | Actual | % Actual / Target |  |  | Actual | Actual | Actual | % Actual / Target |  |  | Actual | Actual | Actual | % Actual / Target |  |  | Actual | Actual | Actual | % Actual / Target |  |  | Actual | Actual | Actual | % Actual / Target |  |  | Actual | % Actual / Target
| At least 65% of capacitated NGOs and CBOs integrated lessons gained from capacity development, learning exchange platform, and innovative practice. | Outcome | 50% | 50% |  |  | 0 | 0% |  | 55% |  |  | 0 | 0% |  | 60% |  |  | 0 | 0% |  | 65% |  |  | 0 | 0% |  | 65% |  |  | 0 | 0% |  | 65% | 0 | 0%
[7 empty] | 0 | #DIV/0! |  |  |  |  | 0 | #DIV/0! |  |  |  |  | 0 | #DIV/0! |  |  |  |  | 0 | #DIV/0! |  |  |  |  | 0 | #DIV/0! |  | 0 | 0 | #DIV/0!
[7 empty] | 0 | #DIV/0! |  |  |  |  | 0 | #DIV/0! |  |  |  |  | 0 | #DIV/0! |  |  |  |  | 0 | #DIV/0! |  |  |  |  | 0 | #DIV/0! |  | 0 | 0 | #DIV/0!