## Logframe
Log-frame
Result Statement | Indicators | Means of Verification | Assumptions
Overall Goal
Improve the quality of education in target communities, leading to enhanced student outcomes and greater community involvement. | - Increase in student literacy and numeracy rates by 20% over three years. | - National standardized test scores. | - Continued government support for education initiatives.
|  | - Project progress reports. | - Availability of resources.
Outcomes
1. Accurate assessment of students' academic performance in target schools. | - Percentage of students achieving grade-level literacy and numeracy at baseline. | - Standardized tests administered to students. | - Willingness of students to participate in assessments.
- Availability of standardized testing materials.
2. Evaluation of teacher qualifications and teaching effectiveness. | - Percentage of teachers meeting national qualification standards. | - Teacher qualification records. | - Teachers’ willingness to share qualifications and participate in interviews.
|  | - Classroom observations and teacher interviews. | - Availability of trained observers.
3. Assessment of school infrastructure and resources. | - Percentage of schools meeting minimum infrastructure standards (e.g., classrooms, libraries, sanitation facilities). | - School facility inspections. | - Accessibility of schools for inspections.
|  | - School records and inventories. | - Availability of up-to-date school records.
4. Analysis of community involvement in education. | - Percentage of parents involved in school activities or governance structures. | - Parent survey results. | - Parents’ willingness to participate in surveys and school activities.
|  | - School committee meeting records. | - Active school governance structures.
Outputs
1.1. Literacy and numeracy tests conducted for students in target schools. | - Number of students tested. | - Test administration records. | - Availability of test administration resources.
| - Test scores disaggregated by gender and grade. | - Completed test forms. | - Coordination with schools for testing schedule.
2.1. Teacher qualifications and training records collected. | - Number of teacher records reviewed. | - Teacher records. | - Cooperation from school administrations in providing access to records.
| - Percentage of teachers with up-to-date qualifications. | - Interview transcripts. | - Accurate record-keeping by schools.
3.1. School infrastructure assessments completed in all target schools. | - Number of schools assessed. | - Inspection reports. | - Safe and accessible routes to schools for assessment teams.
| - Detailed infrastructure assessment reports. | - Photos and diagrams of school facilities. | - Cooperation from school staff during inspections.
4.1. Surveys conducted with parents regarding their involvement in education. | - Number of surveys completed. | - Completed survey forms. | - High response rate from parents.
| - Survey results analyzed and reported. | - Survey analysis report. | - Clear communication of the importance of parental involvement in the study.

## M&E Plan _Example
M&E Plan
Name of the organisation:
Project number:
Project duration:
Project title:
Level | Result Chain | Indicator(s) | Definitions | Indicator Level | Unit of Measurement | Data/Information Need | Baseline | Overal Target | Location/ source of information (where to collect?) | Methods/ tools for data collection (how to collect) | Date (when to collect and analyse?) |  | Responsibility (who collects and analyses?)
[11 empty] | Data collection | Data analysis | Data collection | Data analysis
Overall Objective (OO) | To support the protection of human rights defenders (HRDs), activists, and victims of land grabbing by enhancing their resilience and promoting greater adherence to fair trial standards within the judiciary. | Number of Human Rights Defenders (HRDs), activists, and victims of land grabbing protected from prosecution and harassment | Protected: Utilization of knowledge, including understanding of fair trial rights, court monitoring, physical and digital security, access to materials for digital security, para-legal/legal services, and financial/material assistance to protect against prosecution and harassment | Impact | Number | Number of HRDs protected Number of activists protected Number of land grabbing victims protected
Outcome | Empowered citizens and civil society actors are equipped to assert their legal rights. | Number of university students and HRDs with increased understanding of fair trial rights and their ability to claim these rights | Understanding: This refers to the knowledge of fair trial principles gained by university students through an orientation and mentoring program. This understanding enables them to share or explain these principles to others when needed. Claim: This refers to the students' ability to engage with relevant court staff, police, or other stakeholders about fair trial principles, mechanisms, and processes. | Outcome | Number | Number of university students with increased understanding Number of HRD university students with increased understanding Number of university students able to claim their rights Number of HRD university students able to claim their rights
Output |  |  |  | Output
Output
Output
Output
Output
Output
Output
Output

## M&E Plan_for Practice
M&E Plan
Name of the organisation:
Project number:
Project duration:
Project title:
Level | Result Chain | Indicator(s) | Definitions | Indicator Level | Unit of Measurement | Data/Information Need | Baseline | Overal Target | Location/ source of information (where to collect?) | Methods/ tools for data collection (how to collect) | Date (when to collect and analyse?) |  | Responsibility (who collects and analyses?)
[11 empty] | Data collection | Data analysis | Data collection | Data analysis
Overall Objective (OO) | Improve the quality of education in target communities, leading to enhanced student outcomes and greater community involvement. | - Increase in student literacy and numeracy rates by 20% over three years. |  | Impact
Specific Outcome (SO) | 1. Accurate assessment of students' academic performance in target schools. | - Percentage of students achieving grade-level literacy and numeracy at baseline. |  | Outcome
| 2. Evaluation of teacher qualifications and teaching effectiveness. | - Percentage of teachers meeting national qualification standards. |  | Outcome
| 3. Assessment of school infrastructure and resources. | - Percentage of schools meeting minimum infrastructure standards (e.g., classrooms, libraries, sanitation facilities). |  | Outcome
| 4. Analysis of community involvement in education. | - Percentage of parents involved in school activities or governance structures. |  | Outcome
Output | 1.1. Literacy and numeracy tests conducted for students in target schools. | - Number of students tested. |  | Output
|  | - Test scores disaggregated by gender and grade. |  | Output
| 2.1. Teacher qualifications and training records collected. | - Number of teacher records reviewed. |  | Output
|  | - Percentage of teachers with up-to-date qualifications. |  | Output
| 3.1. School infrastructure assessments completed in all target schools. | - Number of schools assessed. |  | Output
|  | - Detailed infrastructure assessment reports. |  | Output
| 4.1. Surveys conducted with parents regarding their involvement in education. | - Number of surveys completed. |  | Output
|  | - Survey results analyzed and reported. |  | Output

## Indicator tracking Table
Indic